## NCSA Checklist
Activity Checklist
ACTIVITY DATES (Input dates as mm/dd/yy) |  | 2021-07-16 | 2021-07-30
ACTION ITEM | Days Out | Due Date | Date Completed | Actionee | Comments/Details
Deadline for CSA nomination packages | NHQ Set | 2020-10-15 |  | Submitting Regions
Return NCSA Online Data Form Used to populate eServices, webpages, etc. | NHQ Set | 2020-11-15
Activity directors & CSA lineup approved by CAP/CC | NHQ Set | 2020-11-15 |  | NHQ/CPA
Submit first draft of activity budget using template provided | NHQ Set | 2020-09-30
Summer activities announced for the following year | NHQ Set | 2020-11-15 |  | NHQ/CPA
Activities updated in eServices & NCSAS.com | NHQ Set | 2020-11-28 |  | NHQ/CPA
Publish dates for Activity Director and Staff Trainings | NHQ Set | 2020-12-10 |  | NHQ/CPA
AD set up with activity Dropbox folders | NHQ Set | 2020-12-01 |  | NHQ/CPA
Eservices Registration & Payment Opened Members begin applying online | NHQ Set | 2020-12-01 |  | NHQ/CPA
Send invites to any historical staff and potential new staff |  | 2020-12-01
Alternate uniform request deadline (if needed) | NHQ Set | 2021-01-15
Initial application deadline to be considered for priority in placement for primary status most summer activities | NHQ Set | 2021-01-15 |  | NHQ
Oplan 1st Draft Due (NFA Only) | NHQ Set | 2021-01-31
Unit approvals in eServices of online NCSA apps | NHQ Set | 2021-02-01 |  | NHQ
Wing approvals in eServices of online NCSA apps | NHQ Set | 2021-02-15 |  | NHQ
Portions of Registration & Payment turned off to accommodate initial slotting | NHQ Set | 16 Feb - 27 Feb |  | NHQ
Initial slotting accomplished--auto & hand slot | NHQ Set | 17 Feb - 19 Feb
Check to make sure all business rules are applied and make adjustments | NHQ Set | 2021-02-22
Automated slotting announcements to cadet participants/ Unfilled slots may be hand-slotted/may fill slots if cadet notifies they will not accept slot or can't attend | NHQ Set | 2021-03-01 |  | NHQ | After this date, system does not send notice for changes.
Welcome letters & any other documents added to activity websites | NHQ Set | 2021-03-01
NHQ Order Activity Credit Cards | NHQ Set | 2021-03-01 |  | NHQ
NHQ Requests Mission Number (NFA ONLY) | NHQ Set | 2021-03-01 |  | NHQ
Distribute Welcome Letter & additional information to students/staff | NHQ Set | 2021-03-10
Provide Name additional Name for Ops Quals Bypass and 35-6 Data Entry (NFA Only) | NHQ Set | 2021-03-15
Activity credit cards activated, certifications due monthly when purchases are made | NHQ Set | 2021-03-31
Initial student payment deadline for NCSAs | NHQ Set | 2021-03-31
Activity Directors can begin Alternate slotting for those who did not pay deposit or notify you of scholarship/program enrollment or make payment arrangment aggreeable to you | NHQ Set | 2021-04-01
Final student payment deadline for NCSAs | NHQ Set | 2021-04-30
Key Staff identified: Deputy, Finance, Safety | NHQ Set | 2021-01-15
Confirm/follow up re: lodging, facilities, and classrooms | -180 | 2021-01-17
Begin posting engaging content on social media sites | -120 | 2021-03-18
Secure food arrangements | -120 | 2021-03-18
Arrange airport transportation as needed for students | -120 | 2021-03-18
Send any vehicle requests to local wings, regions | -120 | 2021-03-18
Send any equipment requests to NHQ (if applicable) | -120 | 2021-03-18
Start process with base for entry access and update deadlines based on their requirements (if needed) | -100 | 2021-04-07
Send any contracts to NHQ for signature (if applicable) | -90 | 2021-04-17
Confirm lecturers, speakers, VIP's | -90 | 2021-04-17
Initial Schedule deadline | -90 | 2021-04-17
Order Shirts, Coins, etc from Vanguard via NHQ/CPA | -90 | 2021-04-17
Order/print any needed handouts etc.. | -60 | 2021-05-17
Confirm with base re:information needed for entry access (if needed) | -60 | 2021-05-17
Confirm receipt of all forms needed with signatures | -30 | 2021-06-16
Confirm with base entry access is complete and verify where you may enter if multiple gates (if needed) | -15 | 2021-07-01
Send names for Military Support Agreement--MSA (if needed). | -15 | 2021-07-01
Finalized schedule deadline | -15 | 2021-07-01
Create and print Participation (Certificate Template on NCSAS.com) | -5 | 2021-07-11
Create building & facilities layout and point to specific areas | -5 | 2021-07-11
Create and print activity schedule on hard stock and labels | -5 | 2021-07-11
Create name badges (if needed) | -5 | 2021-07-11
Create signs for room locations and exit restrictions | -5 | 2021-07-11
Assign organize facilities, lodging | -5 | 2021-07-11
Pick up facility keys | -1 | 2021-07-15
Conduct RST, ORM, staff training | -1 | 2021-07-15
Assign organize facilities, lodging | -1 | 2021-07-15
Conduct student pick up from airport | 0 | 2021-07-16
Conduct Check-In & Initial Welcome meeting | 0 | 2021-07-16
Formal Welcome Briefing | 1 | 2021-07-17
Conduct online feedback forms/survey for staff and participants (link on ncsas.com) | 6 | 2021-07-22 |  |  | Place time in schedule and do this BEFORE they leave activity.
Enter completion for cadets in eServices using AD Completion Module - mark your DGs as well | 1 | 2021-07-17
Conduct hotwash with staff | 1 | 2021-07-31
Return facility keys, conduct walk-thru, close out with lodging office | 1 | 2021-07-31
Create and distribute thank you letters, submit award recommendations | 14 | 2021-07-30
Post photos on Smugmug and link to FB/social media | 15 | 2021-07-31
Upload Finance Report | 30 | 2021-08-15
Ensure all Safety reporting actions were accomplished | 15 | 2021-07-31
Ensure all files are on activity Dropbox | 45 | 2021-08-30
Activity credit cards turned off | NHQ Set | 2021-09-15
Secure lodging, facilities & dates for next year | 75 | 2021-09-29
After Action Report Due and AD Completion Module Deadline | NHQ Set | 2021-09-30
First draft budget for next year due (for appropriated $$ - need 2 years out) | NHQ Set | 2021-09-30
NHQ will move Dropbox folders to a "ZZ" archive | NHQ Set | 2021-10-01
Begin coordination of staff summary recommending next year's activity directors/ Solicit CSA nominations from Regions/Wings | NHQ Set | 2021-10-01
Formulas:
Due Date = C3+[Days Out]
Due Date = D3+[Days Out]
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Insert activity start date
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Enter activity end date

## Day 1
| Agenda | Today's Notes
| x/xx/2021 - Saturday | Travel Day
0630
45
0700
15
30
45
0800 | Required Staff Training
15
30 |  |  | Notes:
45 |  |  | 1. Bars are used to indicate time blocks
0900 | Pick up cadets |  | 2. Items listed in Column C are examples
15 | In-processing
30
45
1000
15
30
45
1100
15
30
45
1200
15
30
45
1300
15
30
45
1400
15
30
45
1500
15
30
45
1600
15
30
45
1700
15
30
45
1800
15 | Course Introduction
30 | Activity Safety Briefing
45
1900
15
30
45
2000
15
30
45
2100
15
30
45
2200 | Room check
30 | Lights out

## Day 2
| Agenda | Today's Notes
x/xx/2021 - Sunday
0630
45
0700
15
30
45
0800
15
30
45
0900
15
30
45
1000
15
30
45
1100
15
30
45
1200
15
30
45
1300
15
30
45
1400
15
30
45
1500
15
30
45
1600
15
30
45
1700
15
30
45
1800
15
30
45
1900
15
30
45
2000
15
30
45
2100
15
30
45
2200 | Room check
30 | Lights out

## Day 3
| Agenda | Today's Notes
x/xx/2021 - Monday
0630
45
0700
15
30
45
0800
15
30
45
0900
15
30
45
1000
15
30
45
1100
15
30
45
1200
15
30
45
1300
15
30
45
1400
15
30
45
1500
15
30
45
1600
15
30
45
1700
15
30
45
1800
15
30
45
1900
15
30
45
2000
15
30
45
2100
15
30
45
2200 | Room check
30 | Lights out

## Day 4
| Agenda | Today's Notes
x/xx/2021 - Tuesday
0630
45
0700
15
30
45
0800
15
30
45
0900
15
30
45
1000
15
30
45
1100
15
30
45
1200
15
30
45
1300
15
30
45
1400
15
30
45
1500
15
30
45
1600
15
30
45
1700
15
30
45
1800
15
30
45
1900
15
30
45
2000
15
30
45
2100
15
30
45
2200 | Room check
30 | Lights out

## Day 5
| Agenda | Today's Notes
x/xx/2021 - Wednesday
0630
45
0700
15
30
45
0800
15
30
45
0900
15
30
45
1000
15
30
45
1100
15
30
45
1200
15
30
45
1300
15
30
45
1400
15
30
45
1500
15
30
45
1600
15
30
45
1700
15
30
45
1800
15
30
45
1900
15
30
45
2000
15
30
45
2100
15
30
45
2200 | Room check
30 | Lights out

## Day 6
| Agenda | Today's Notes
x/xx/2021 - Thursday
0630
45
0700
15
30
45
0800
15
30
45
0900
15
30
45
1000
15
30
45
1100
15
30
45
1200
15
30
45
1300
15
30
45
1400
15
30
45
1500
15
30
45
1600
15
30
45
1700
15
30
45
1800
15
30
45
1900
15
30
45
2000
15
30
45
2100
15
30
45
2200 | Room check
30 | Lights out

## Day 7
| Agenda | Today's Notes
x/xx/2021 - Friday
0630
45
0700
15
30
45
0800
15
30
45
0900
15
30
45
1000
15
30
45
1100
15
30
45
1200
15
30
45
1300
15
30
45
1400
15
30
45
1500
15
30
45
1600
15
30
45
1700
15
30
45
1800
15
30
45
1900
15
30
45
2000
15
30
45
2100
15
30
45
2200 | Room check
30 | Lights out

## Day 8
| Agenda | Today's Notes
| x/xx/2021 - Saturday | Travel Day
0630
45
0700
15
30
45
0800
15
30
45
0900
15
30
45
1000
15
30
45
1100
15
30
45
1200
15
30
45
1300
15
30
45
1400
15
30
45
1500
15
30
45
1600
15
30
45
1700
15
30
45
1800
15
30
45
1900
15
30
45
2000
15
30
45
2100
15
30
45
2200
30

## Working Log
Working Log
Note: Used to track details per sortie (e.g., phone calls, agreements, dining facility/museum/other hours, POC emails/phone #s, reminders, security, other…)
Done | Location or Activity | Action | Results | Date
þ | Location/ Activity 1
Location/ Activity 2
Location/ Activity 3
Location/ Activity 4
Location/ Activity 5
þ | Location/ Activity 6
Location/ Activity 7
Location/ Activity 8
Location/ Activity 9
Location/ Activity 10
Guest Speakers
Evening Sessions

## Schedule
Activity Name
USAF Civil Air Patrol
Use this form to build your final activity schedule, delete extra columns/rows, then resize for printing to 1 page
x/xx/2021 - Sunday | x/xx/2021 - Monday | x/xx/2021 - Tuesday | x/xx/2021 - Wednesday | x/xx/2021 - Thursday | x/xx/2021 - Friday | x/xx/2021 - Saturday
UOD: | UOD: | UOD: | UOD: | UOD: | UOD: | UOD:
0700 Breakfast | 0630 Breakfast | 0700 Breakfast | 0700 Breakfast | 0630 Breakfast | 0630 Breakfast | 0630 Breakfast
0800 Religious observance (optional) - location | 0730 Formation / Departure | 0745 Formation / Departure | 0745 Formation / Departure | 0730 Formation / Departure | 0730 Formation / Departure | 0730 Formation / Departure
0830 Formation / Departure | 0800 Location/activity | 0910 Location/activity | 0915 Location/activity | 0800 Location/activity | 0800 Location/activity | 1000 Location/activity
0900 Location/activity |  |  | Location/activity | Location/activity | Location/activity | Location/activity
1130-1230 Lunch - (location) | 1130-1215 Lunch - (location) | 1030-1100 Lunch - (location) | 1130-1230 Lunch - (location) | 1130-1230 Lunch - (location) | 1130-1230 Lunch - (location) | Box lunches during break
1300-1530 Location/activity | 1230 Location/activity | 1115 Location/activity | 1300 Location/activity | 1300 Location/activity | 1300 Location/activity | 1230-1400 Location/activity
| 1530 Location/activity | 1300 Location/activity | 1430 Location/activity | 1330 Location/activity | 1330 Location/activity | 1600 Location/activity
1700-1800 Dinner - (location) | 1700-1800 Dinner - (location) | 1700-1830 Dinner - (location) | 1730-1830 Dinner - (location) | 1700-1800 Dinner - (location) | 1700-1800 Dinner - (location) | 1800 Reception
1800 Free time | 1800 Free time |  |  | 1800 Free time | 1800 Free time | 1830 - Buffet dinner
1900 Location/activity | 1900 - Location/activity | 1900 - Location/activity | 1900 - Location/activity | 1900 - Location/activity | 1900 - Location/activity | 1900 - Location/activity 1915 - Director speech
| 2030 Free time | 2030 Free time | 2030 Free time | 2030 Free time | 2030 Free time | 1930 - Graduation and Awards
2200 - Lights out | 2200 - Lights out | 2200 - Lights out | 2200 - Lights out | 2200 - Lights out | 2200 - Lights out | 2200 - Lights out

## Agendas
Staff Telecon Agendas
NOTE: Use to build an agenda for staff telecons. Then copy/paste the appropriate agenda block into the invitation to staff members
xx February 2019 |  | xx March 2019 |  | xx April 2019
Staff Telecon Agenda: | Notes | Staff Telecon Agenda: | Notes | Staff Telecon Agenda | Notes
xx May 2019 |  | xx June 2019 |  | xx July 2019
Staff Telecon Agenda | Notes | Staff Telecon Agenda | Notes | Staff Telecon Agenda | Notes

## POCs
Points of Contact
NOTE: Instructors, suppliers, security, excursion POCs, dining facilities, NHQ. Get cell #s for JIT calls & addresses for thank you notes.
Facility | Contact | Email | Phone | Notes